Antalaha, simulation exercise (D. Ledesma)

Report

Community Shelter Kit/Madagascar mission

30.07.2019

Table of Contents

1. General information

1.1   Project/mission title

1.2   Country

1.3   Report date

1.4   Type of operation

1.5   Requesting Organization

2. Context

3. Outcomes

4. Outputs

5. Activities

5.1   Defining requirements

5.2   Methodology

Work in progress

Seeing CSK as product

5.3   State of the art

Standard Product Catalogue

Wathab

Shelter and construction Materials

5.4   SYNTHEZE

Cleaning kits

Combined items

5.5  DESIGN

Quick prototyping

Prototype validation

Workshop

SIMEX

6. The community Shelter Kit

6.1   General Information

6.2   List of Items

6.3   Logistics and price

6.4   Items description

6.5   Prepositioning items

7. Conclusions

7.1   Climatic and geographic context

7.2   Community Shelter Kit response

7.3   Operational flexibility

8. Operational challenges

8.1   Inside country restrictions

8.2   Time frame

8.3   Geographic limitations

9. Recommendations

9.1   Regional expansion

9.2   Replication and adaptation

9.3   Training packages

10. Annexed documents

10.1   Service agreement

10.2   ToR for Madagascar mission

10.3   List of contacted people during de mission

1. General Information

1.1 Project/mission title: Community Shelter kit

1.2 Country: Africa Region / Madagascar

1.3 Report date: 30.07.2019

1.4 Type of operation: Research and Development

1.5 Requesting Organisation: « Aide Internationale de la Croix-Rouge Luxembourgeoise » (AI-CRL)

2. Context

The tropical and subtropical regions of Africa are regularly affected by natural disasters. The African Red Cross National Societies are often called upon to intervene on the frontline during each crisis. There is therefore a need to equip them with a shelter solution that is thought out in a participatory and innovative way, both before the production and design of materials and in terms of effectiveness and usability.

With regard to Shelter emergency response tools available to the international humanitarian community, the most common used scale to date is the family shelter kit. To date, no standard kit with an effective response at community level has been developed.

AI-CRL hereby requests the IFRC-SRU to conduct a Research & Development study (R&D)  to develop a context based Community Shelter Kit (CSK) adapted to the predefined context of the rural communities in the humid tropical region of Africa.

3. Outcomes

This R&D project intends to improve the first community response supporting future emergency shelter operations and improving the resilience of the population affected.

The focus has been placed on the design and development of a contextualized Community Shelter Kit adapted to rural communities in the tropical and subtropical regions of Africa. The final product is named Community Shelter Kit (CSK).

4. Outputs

The following objectives were achieved during this R&D project and the Madagascar mission.

Specific needs were documented and defined

A specific participatory methodology was defined

A technical study on the composition of available kits in the Red Cross was carried out

A quick prototype was created

Specific process of validation carried out

Final prototype defined

Product sheet for the Community Shelter Kit have been developed

5. Activities

The project activities and mission were performed in collaboration and with the support of AI-CRL and Croix-Rouge Malagasy (CRM) following the agreed methodology and ToR for this project and the mission in particular.

  - Defining the requirements

A set of participatory sessions were conducted by the IFRC-SRU together with AI-CRL.

The first session defined the requirements for designing the CSK including specific requests from AI-CRL such as appointed country and particular context.

The second sessions focused on the predefinition of expected functions for the CSK and agreement on the proposed methodology.

The outputs of these participatory sessions are summarized in the following design bases:

Predefined bases of design

- Context: Rural communities of Africa in humid forest environment

- Type of associated disaster: Cyclones – floods

- Type of response: immediately after the disaster unset-before international aid

- Upon request of AI-CRL the designated country for field testing is Madagascar

- Modification of the target community size from 10000 to 500 people max.

- Upon request of AI-CRL no mechanic tools nor tools that require maintenance to be included in the CSK

- Key factors are transportability and prepositioning of the kit

- Users are villagers with no specific training

The functions agreed:

- Heavy cleaning/ Tree removal + debris removal including adobe, wood, CGI and other construction materials

- Light cleaning/ water pumping, mud and debris removal

- Protection/ individual and collective protection elements

5.2 Methodology

The proposed methodology is based on the following steps:

Work Process

The work process was structured into 3 chapters (spaces) that are inspired and focus in the product itself. Discover, Design and Deliver the product from a specific and defined point of view.

In the “space” DISCOVER, the activity focused on researching and analyzing the available solutions. The challenge of the activity is to understand the diversity and potential of the different available solutions.

Mock-up or Design is the “space" of the creativity and sharing experiences. The participation of different actors provided a rich matter to scale down the prototype. The prototype is validated with a set of simulation exercises in Madagascar.

Formalization is the key of the DELIVER “space”. Process the recorded information during the mission to Madagascar and produce a final report about the kit composition including BoQ and material descriptions were the main outputs to be delivered.

| DISCOVER | MOCK-UP | DELIVER |
| --- | --- | --- |
| State of the art Identify available Solutions Collect user experiences History, what has been done? | Design UX inclusion Participatory approach with added experiences (Functional analyze) All positive ideas welcome | Recording UX UY Feedback after the exercise |
| Synthetize Filter the information Summary of the information in a predefined analytical manner | Verification Simulation exercise in Madagascar Including daft product design & participatory experience with final users (Functional analyze) Wrap-up the ideas and tuning the prototype if needed Final documentation for prototyping | Implement Final definition and BoQ Documentation |

Seeing the Community Shelter kit as a product

Product: “A thing or person that is the result of an action or process” (https://en.oxforddictionaries.com/)

Product conceptualization

Technology Feasibility

Process

Innovation

Function

Experience

Community Shelter Kit

Result

Viability & Impact

Human

Usability

Identity

Promotion

The product approach was inspired in a “model” or representative example previously tested. This process of analysis of the model, attempted to identify the elements that provide an additional potentiality for the project and the future product.

The structure to define the CSK included three dimensions that define the product providing a different but complementary vision that focusses on Human (user), Technology (Capacities) and Results (viability) of the project or final product.

This 360’ vision also included an innovative benefit with the user experience, the identity of the product and the final promotion of the results.

5.3 State of the art - Getting context information

Standard Product Catalogue (previously Emergency item catalogue)

The Standard Product Catalogue (SPC) was established by the International Federation and the International Committee of the Red Cross, with the support of National Societies. Its aim is to standardize and harmonize the selection and procurement of relief items during emergency operations.

The current online management system and the dedicated website enable a permanent data update, open accessibility, and transparency for all users.

http://itemscatalogue.redcross.int/

The catalogue is intended to facilitate the selection and acquisition of the suitable items and provide guidance and assistance to: operational users and decision makers, donors and national organizations. In this sense, the Website is the common used access point to the users of the SPC.

In the website the items are organized in five major categories: ERU and RDU, Food and Livelihood, Health, Logistics, and Water and Habitat (WATHAB). Each one of the mayor categories is structured in a different group of items according to standardization and operational criteria.

Therefore, the SPC is a reference for the Red Cross and Red Crescent Movement in terms of emergency items, standardization, purchasing and availability of products commonly used during humanitarian operations.

Definitions

The research, considered the following definitions:

KIT: a collection of equipment tools and often supplies typically carried in a box or bag and used for a variety of activities (eg. welder kit).

SET: the complete apparatus or equipment used in a particular predefined process (eg. set of drugs for cholera treatment)

The research

The summary research focussed on the different available kits that can be related or inspire the future development of a “Community Shelter Kit”.

In order to facilitate the comprehension of the collected information and for this particular stage, the category ERU and RDU are excluded from the present analysis. Currently there is no Shelter/construction ERU or RDU unit.

Identified Kits in the SPC

Over 160 kits were identified in the SPC.

The next graph shows the distribution of the kits in percentage according to the categories.

The category with more kits is Health and the one with less is Food and Livelihood.

*Note: notice that the table only shows the named identified kits. For the particularities of the Health category there are available an important group of sets that are not included here.

The WATHAB category

WATHAB is in second place with 36% of the identified kits (59 in total).

This percentage shows the relevance in terms of kit availability, standardization and logistics that the WATHAB category has in the SPC.

This category includes Water and Sanitation but also Shelter (Habitat) components. The following graph shows the distribution of kits inside the WATHAB category.

The Shelter and construction materials component has 22% with 13 over 59 identified kits in the category.

| WATHAB kit distribution |  |
| --- | --- |
| SHELTER and construction Materials | 13 |
| WATER & SANITARION | 46 |
| TOTAL WATHAB | 59 |

WATHAB – Shelter and construction materials

The "Shelter and construction materials" section in the catalogue are organized with the following structure:

- Collective Service Tent

- Construction Materials

- Family tents, tarpaulin and accessories

- Shelter and construction kits

A wide range of materials, sets and kits are distributed in the four different categories.

Two specific kits in Family tents, tarpaulin and accessories were identified. The rest of the 11 identified kits can be found under Shelter and constructions kits.

The following matrix shows in detail the identified kits organized with the same structure and keyword that appears in the web catalogue.

WATHAB – Shelter and construction materials

Key: Shelter and construction materials, Collective service tent

No kit identified

Key: Shelter and construction materials, construction materials

No kit identified

Key: Shelter and construction materials, Family tents, tarpaulin and accessories

Winterisation kit for Family tent

Winterisation kit for Family tent framed

Key: Shelter and construction materials, Shelter and construction kits

Bamboo kit

Carpenter kit

Cleaning Kit

Cover kit

Mason kit

Plastic Sheeting for windows

Rubble removal kit

Sahel Shelter kit

Shelter kit

Shelter tool kit

Steel kit

5.4 SYNTHEZE

WATHAB kit classification

To better understand the identified kits in the catalogue, the key words were organized in a “tree” structure, starting from the body of the "Shelter and construction materials" to be divided in different branches.

The next graph illustrates this structure.

Shelter kit

Carpenter kit

Cover kit

Mason kit

Bamboo kit

Plastic sheeting for windows kit

Steel kit

Specific constructions and kits

Trade/craft and kits

Cleaning kit

Kits for tents

Rubble removal kit

kits

Winterization kits X2

Shelter kit Construction

ts

Kits for Cleaning

ts

Shelter and construction materials

From the main body we defined three branches, kits for tents, kits for construction and kits for cleaning, each of them with individual kits. Following this classification the distribution of kits result as follows: 2 kits for tents; 9 kits for construction and 2 kits for cleaning.

The next graph shows the numbers and distribution in percentage.

Cleaning kits

During the definition phase of the base of design, the main functions for the CSK were identified as: Heavy Cleaning, Light Cleaning, Protection and communication.

The two identified kits for cleaning are Cleaning kit and Rubble removal kits.

The first one has 27 different items and the second 28 items. All the items can be found in the Standard Product Catalogue with the particular code and specifications in a separate space.

The next matrix shows the identified items per kit

|  | Kits for cleaning |
| --- | --- |
| Cleaning Kit | BROOM, push broom type, 45cm width, without handle |
|  | BROOM, straw brush, 30cm width block, without handle |
|  | BROOM, scrubbing brush, 30cm width block, without handle |
|  | FLOOR BLADE, squeegee, rubber, 45cm, without handle |
|  | BROOM, floor washing broom, long handle |
|  | MOP-HEAD, head only, without stick |
|  | MOP-STICK, stick only, without head |
|  | BROOM HANDLE, 120cm in 4 sections, with standard threads |
|  | FLOOR CLOTH, cotton, 50 X 50cm |
|  | BRUSH, SCRUBBING, hand brush |
|  | SPONGE, reinforced cellulose, 5 x 10 x 15cm |
|  | DUST PAN |
|  | DETERGENT, household, general cleaning, concentrate for 1L |
|  | DETERGENT, household, general cleaning, liquid, bottle 1L |
|  | DETERGENT, household, multipurpose, liquid, 5L |
|  | CHLORINE,1000mg (NaDCC 1670mg) multipurpose,1 tab DGR IF>5KG |
|  | MASK, vapor and dust protection, FPP2 disposable half mask |
|  | BOOTS, heavy duty plastic rubber, pair, size 44 |
|  | OVERALL, disposable, white, non woven fireproof, size XXL |
|  | GLOVE, protection, heavy duty soft leather, size 11, pair |
|  | GLOVE, cleaning, rubber, large |
|  | GLOVES, chemical protection, heavy duty rubber,size 10 pair |
|  | BAG, PE plastic, for garbage, 100L, black, 0.07mm |
|  | BAG, PE plastic, for rubble, 100L, black, 0.15mm |
|  | BUCKET, heavy duty rubber, masonery type |
|  | BUCKET, metal, galvanised, 25l |
|  | BAG, coated woven PE, for rubble, 100L, 100g/m2 |
| Rubble removal kit | ROPE, POLYPROPYLENE, black, diam. 12mm, twisted |
|  | TAPE ADHESIVE, canvas reinforced, 50mmx50m roll, silver |
|  | TIE WIRE, galvanised, diam. 1.5 mm, 25m, roll |
|  | BROOM, push broom type, 45cm width, without handle |
|  | FLOOR BLADE, squeegee, rubber, 45cm, without handle |
|  | DUST PAN |
|  | SLEDGE HAMMER, hardened steel, wood handle, 4800g, 900mm |
|  | SLEDGE HAMMER, hardened steel, wood handle, 1200g, 250mm |
|  | PICK-AXE, with handle |
|  | WHEEL BARROW, approx. 90L dry solids, strong solid wheel |
|  | DIGGING BAR, in 2 pieces with thread joint, 1.6m |
|  | CROWBAR, with angled beak, 300 mm length |
|  | CROWBAR, with angled beak, 500 mm length |
|  | CHISEL, flat 20mm, for masonry, 300mm length |
|  | AXE, 1kg head, with safety handle |
|  | SHOVEL, round point with Y handle, total lenght approx.1m |
|  | MASK, vapor and dust protection, FPP2 disposable half mask |
|  | BOOTS, heavy duty plastic rubber, pair, size 44 |
|  | HELMET, builder, plastic, white, size 51-62 |
|  | GOOGLES, plastic, with rubber string, eyes protection |
|  | GLOVE, protection, heavy duty soft leather, size 11, pair |
|  | GLOVE, cleaning, rubber, large |
|  | GLOVES, chemical protection, heavy duty rubber,size 10 pair |
|  | BAG, PE plastic, for garbage, 100L, black, 0.07mm |
|  | BUCKET, heavy duty rubber, masonery type |
|  | BUCKET, metal, galvanised, 25l |
|  | BAG, coated woven PE, for rubble, 100L, 100g/m2 |
|  | STICK, broom handle |

The “Cleaning kit” has a specific items composition to be used with a hygienic cleaning purposes (interior cleaning, housing in general, etc.). The “Rubble removal kit” items are closer to the construction tools, with a clear profile to be used for the clearance of raw heavy materials (construction materials, soil, mud and debris in general).

Common items (duplicated)

There are 12 identified items that are common for the two cleaning kits.

Combining items

A direct combination of the unique items from the two kits for cleaning into a new list provides a certain complementarity in terms of use without having duplication on the items.

Because of this combination, we have a complete kit of 43 different items with no duplications.

The items are classified into different groups regarding the basic or primary use. The proposed classification is packing and tying items, Personal protection, tools, hygienic cleaning, and disinfection.

The graph shows the distribution of the combined items in function of the proposed classification.

The next table shows the final list of the combined items.

List of combined items

BAG, PE plastic, for garbage, 100L, black, 0.07mm

BAG, PE plastic, for rubble, 100L, black, 0.15mm

BAG, coated woven PE, for rubble, 100L, 100g/m2

TAPE ADHESIVE, canvas reinforced, 50mmx50m roll, silver

BOOTS, heavy duty plastic rubber, pair, size 44

GLOVE, protection, heavy duty soft leather, size 11, pair

GLOVES, chemical protection, heavy duty rubber,size 10 pair

GOOGLES, plastic, with rubber string, eyes protection

HELMET, builder, plastic, white, size 51-62

MASK, vapor and dust protection, FPP2 disposable half mask

OVERALL, disposable, white, non woven fireproof, size XXL

TIE WIRE, galvanised, diam. 1.5 mm, 25m, roll

BUCKET, heavy duty rubber, masonery type

CHISEL, flat 20mm, for masonry, 300mm length

CROWBAR, with angled beak, 300 mm length

CROWBAR, with angled beak, 500 mm length

DIGGING BAR, in 2 pieces with thread joint, 1.6m

SLEDGE HAMMER, hardened steel, wood handle, 1200g, 250mm

SLEDGE HAMMER, hardened steel, wood handle, 4800g, 900mm

WHEEL BARROW, approx. 90L dry solids, strong solid wheel

BUCKET, metal, galvanised, 25l

FLOOR CLOTH, cotton, 50 X 50cm

STICK, broom handle

BROOM HANDLE, 120cm in 4 sections, with standard threads

BROOM, push broom type, 45cm width, without handle

BROOM, scrubbing brush, 30cm width block, without handle

BROOM, straw brush, 30cm width block, without handle

BROOM, floor washing broom, long handle

DUST PAN

FLOOR BLADE, squeegee, rubber, 45cm, without handle

MOP-HEAD, head only, without stick

MOP-STICK, stick only, without head

BRUSH, SCRUBBING, hand brush

SPONGE, reinforced cellulose, 5 x 10 x 15cm

DETERGENT, household, general cleaning, liquid, bottle 1L

DETERGENT, household, multipurpose, liquid, 5L

DETERGENT, household, general cleaning, concentrate for 1L

GLOVE, cleaning, rubber, large

ROPE, POLYPROPYLENE, black, diam. 12mm, twisted

PICK-AXE, with handle

AXE, 1kg head, with safety handle

SHOVEL, round point with Y handle, total lenght approx.1m

CHLORINE,1000mg (NaDCC 1670mg) multipurpose,1 tab DGR IF>5KG

5.5 Design

Quick Prototyping

The “quick prototyping” process was organized through a set of exchanges with experts and suppliers with different profiles. The same content was explained in these exchanges focused on the needed tools to perform the predefined functions of the CSK. The quick prototype list resulted in a combination of the list of tools identified from SPC “list of combined items” and the inclusion of specific tools suggested during the exchanges with experts and suppliers.

The following table shows the composition of the “quick prototype”

| Quick Prototype Items list |  |
| --- | --- |
| 1 | BAG, coated woven PE, for rubble, 100L, 100g/m2 |
| 2 | BOOTS, heavy duty plastic rubber, pair, size 44 |
| 3 | GLOVE, protection, heavy duty soft leather, size 11, pair |
| 4 | GOOGLES, plastic, with rubber string, eyes protection |
| 5 | HELMET, builder, plastic, white, size 51-62 |
| 6 | MASK, vapour and dust protection, FPP2 disposable half mask |
| 7 | TIE WIRE, galvanised, diam. 1.5 mm, 25m, roll |
| 8 | BUCKET, heavy duty rubber, masonry type 10l |
| 9 | BUCKET, heavy duty rubber, masonry type, TWO HANDELS 30l |
| 10 | CHISEL, flat 20mm, for masonry, 300mm length |
| 11 | CROWBAR, with angled beak, 500 mm length |
| 12 | DIGGING BAR, 1.6m |
| 13 | SLEDGE HAMMER, hardened steel, wood handle, 1200g, 250mm |
| 14 | SLEDGE HAMMER, hardened steel, wood handle, 4800g, 900mm |
| 15 | WHEEL BARROW, approx. 90L dry solids, strong solid wheel |
| 16 | FLOOR CLOTH, cotton, 50 X 50cm |
| 17 | SAW, bow type, for wood, 750mm blade from green wood |
| 18 | Two man crosscutting hand saw 122cm 3kg |
| 19 | Hand saw "revers cutting" for bamboo + green wood |
| 20 | Machete wood XP 51cm |
| 21 | BROOM, floor washing broom, long handle |
| 22 | DETERGENT, household, multipurpose, liquid, 5L |
| 23 | ROPE, POLYPROPYLENE, black, diam. 12mm, twisted |
| 24 | ROPE, NYLON, polyamide, diam. 6 mm, braided |
| 25 | PICK-AXE, with handle |
| 26 | AXE, 1kg head, with safety handle |
| 27 | SHOVEL, round point with Y handle, total length approx.1m |
| 28 | Hand/foot power water pomp with flexible pipes and connections included |
| 29 | Power puller with tendon and hook, max, load 3000k |
| 30 | First aid kit |
| 31 | Tie down ratchet with Hook (ratchet-strap) |
| 32 | Tarp 4x6 standard IFRC |
| 33 | Nails (idem Shelter tool kit)+ Hamer + clippers |
| 34 | Measuring tape 5m |
| 35 | Measuring tape 50m |
| 36 | Shade net roll |
| 37 | Head lights with batteries and solar charger |
| 38 | LADDER, aluminium extendable in 2 parts, 4.5m |
| 39 | MEGAPHONE, 25W, connect. on cigar lighter |

Prototype validation

A process was designed to validate the “quick prototype” by the future users and change the scale into a minimum viable product.  AI-CRL appointed Madagascar as the country for the validation mission.

The validation process was structured in two dimensions

- Prototype composition – Community validation

Workshops session to validate the quick prototype hypothesis and produce a comparable list of tools and materials

- Prototype usability – Empiric validation

A set of three different simulation exercises to validate the usability of the prototype and exchange with users about their experience

Workshop in Antalaha

The workshop was a key factor for the community verification of needs and capacities hypothesis used in the design of the prototype. The main activity focusses with particular attention on the composition of the tools and materials agreed by the participants.

Numbers with people on board

Date: 08.07.2019

Place:  ”Chambre de commerce Antalaha”

15 participants = 8 RC volunteers + 3 community rep. + 4 villagers

Additionally 5 CRM/CRL team members and President CRM regional branch complete the participants list

Agenda

Content or activity

Open workshop presentation and code of conduct

Introduction of CRM + CRL+SRU + Project

4 groups- Define limits activity + presentation

Break

Experience exchange and summary with common points

Objectives- activities / Actors relations

Lunch break

Group Presentation

Matrix - Activities organized in Functions

Prioritization of functions

Functions materials activity per group

Group presentation

Summary in to a common list

Day evaluation

Closing the workshop

Dynamics and first list/conclusions

The workshop activities were based on a set of participatory sessions using the basic concepts of the Functional Analysis procedure.

The 6 sessions were conducted by the SRU together with MRC/CRL team.

During the sessions, the activities where organized as follows:

- Limits: questions focussing on When? Where? and How? the CSK is designed for.

- Use of the CSK: what the CSK has to do? What are the activities that the CSK has to support? What are the needs that the CSK has to cover?

- Functionality of the CSK: organize the needs, activities and actions defined before into the functions that the CSK has to support

- Prioritization of the defined functions

- List the tools and materials needed per each function

- Compilation and validation of a common agreed list of tools

During the workshop, the participants were organized into three groups that first work individually to later share the reflection and document the agreed points.

All the activities were supported with PPT presentations and documented in a flipchart.

The final agreed and documented list of tools was the main output of the workshop. The workshop list validates most of the tools identified in the quick prototype previously designed.

The next table shows the list of validated tools during the workshop

| Tool list validated during the Workshop |  |
| --- | --- |
| 1 | Hammer |
| 2 | Rope |
| 3 | Level |
| 4 | Square |
| 5 | Measuring tape |
| 6 | Planer cut |
| 4 | Bit brace |
| 7 | Stairs |
| 8 | Chisel |
| 9 | Hand plane |
| 10 | Metallic bar/ digging bar |
| 11 | Shovel |
| 12 | Spade |
| 13 | Rake |
| 14 | Digging fork |
| 15 | Brum |
| 16 | Bucket |
| 17 | Will Barrow |
| 18 | Pike |
| 19 | Axe |
| 20 | Mechanic hand saw |
| 21 | Woodworking saw |
| 22 | Nails |
| 23 | Tarpaulin |
| 24 | Globes |
| 25 | Helmet |
| 26 | Mask |
| 27 | Boots |
| 28 | Soap |

Additionally the list of materials agreed during the workshop is a solid base to support the current project of MRC/CRL with a community kit component.

Antalaha workshop

SIMEX

During the mission, a series of simulation exercises were carried out to exchange the user experience and validate the composition of the kit. Each simulation represented a previously defined situation in which the CSK would be deployed.

Scenarios were prepared beforehand according to predefined needs (see table below).

The activities organized with the same structure are the following:

- Introductory meeting explaining the objectives and definitions

- Download and open the kit from the truck

- Free work of volunteers in the requested activities

- Special explanations and demonstrations on request

- Open session after work with questions and answers

SIMEX I

Numbers

Three communities engaged

Rural, semi-rural and urban context identified

55 + participants (Red Cross volunteers and villagers)

Upon request trainings and explanation delivered

Five MRC/CRL staff full time involved

Pickup for transportation of materials and participants

Scenarios definition

| SENARIO | CONTEXT | CHALENGE |
| --- | --- | --- |
| SIMEX I Block road | RURAL Land slide Big tree blocking the road Obstacles eg. big rocks | Move heavy objects Move big volumes Clean open areas to use |
| SIMEX II Flooded space | URBAN Flooded space Mud + water Debris small size construction materials | Water extraction Mud and debris removal Clean for access and safe use |
| SIMEX III Collapsed building | SEMI-RURAL Different type of debris Big construction materials Structure collapsed or seriously damaged | Safety work Clean access Move debris and construction materials Classification/reutilization Reconstruction/emergency construction |

SIMEX III

Workshop

SIMEX II

SIMEX I

ANTALAHA

SAVA region

ANTSIRANANA Province

Identification

With the support of the local MRC/CRL team, the three different sites were identified. Each site is associated with a different commune and responds to predefined context criteria.

A variety of rural, semi-rural and urban site environments attempt to represent the different contexts in which the Community Shelter Kit would be used.

SIMEX 1

Location and scenario

The SIMEX 1 was located in a rural village 2 hours distance from Antalaha during dry season.

Exact location S15° 2’ 37” , E50° 20’ 38”

SIMEX 1

50m of block road

SIMEX I location

The scenario was prepared one day in advance blocking more than 50m of road with big trees trunks, sand, rocks, branches and other forest elements

SIMEX I

SIMEX Follow up

- Introductory meeting explaining the objectives and definitions

The introductory session conducted in place with participation of the 10 appointed volunteers. Additionally attendees such as head of village and community representing from neighbored villages participated. The proposed challenge was to clean (unblock) the road.

SIMEX I Explaining session

- Download and open the kit from the truck

The “quick prototype” fits in one pickup that allows easy downloading of the tools.

First contact of the volunteers with the tools, bags and different packaging.

Classification of the known and unknown tools “useful/useless”

Particular interest from the volunteers in the individual protection tools (cask, gloves, mask, boots, etc.)

SIMEX I Simulation in progress

- Free work of volunteers in the requested activities

The volunteers worked freely with no external indications with the main objective to clean the road.

The 10 volunteers naturally organized in smaller groups according to their own physical capacities (stronger volunteers heavy works)

Heavy objects where moved by using more people. Alternative/innovative techniques were discarded for lack of knowledge about the use or the tool itself.

Volunteers show a particular interest in the arch hand saw.

SIMEX I How to use a pulley

- Special explanations and demonstrations on request

Particular explanations and demonstrations were delivered on the use of pulleys and levers with drag bars.

Individual explanations were given on the use of individual protection tools.

The use of the arch hand saw and the procedure to change the blades was shown upon request.

SIMEX I individual security items

- Open session after work UX comments and exchanges

The volunteers team composed by ten young man showing their strong physical capacity to move heavy objects.

In general curious about new materials but reluctant to use it for the simulation exercise.

The exception was the hand arch saw that was used to cut tree branches.

Material difficult to identify inside the plastic sacs with no graphic information

They find the pulley system interesting for daily work but need specific training for use during emergency context

Tools for individual safety perceived as luxurious elements that provide good image but not necessary

Requested tools, rake and long handle axe

Other tool comments:

Shovel with rectangular head and long handle

Machete sharped and square head

Brush strong and long handle

- Used tools

| SIMEX I | USED ITEMS |
| --- | --- |
| 1 | Crow bar |
| 2 | Digging bar |
| 3 | Axe |
| 4 | Arch hand saw |
| 5 | Machete |
| 6 | Shovel (all models) |
| 7 | Wheelbarrow |
| 8 | PE bags |
| 9 | Brush |
| 10 | Cask |
| 11 | Mask |
| 12 | Gloves |
| 13 | Goggles |
| 14 | Rope 10mm |
| 15 | Pulley |

SIMEX 2

Location and scenario

The SIMEX 2 was located in an urban neighborhood of Antalaha.

SIMEX 2

Affected building

Flooded space

Exact location S14° 54’ 46” , E50° 16’ 58”

The scenario was prepared one day in advance inside of a damaged building adding mud, debris, big rocks, trunks, truck wheels, construction materials and water. Finally, the access to the building was blocked with a rocks. The water was pumped from a near borehole using the foot water pump included in the “quick prototype” set. Specific demonstration was required to use the pump.

SIMEX II

SIMEX Follow up

- Introductory meeting explaining the objectives and definitions

Introductory session conducted in place with participation of the 10 appointed volunteers (4 men and 6 women). No additional participation of external people. The proposed challenge was to clean the interior space of the affected construction to be used as a space for collective shelter.

SIMEX II Introduction

- Download and open the kit from the truck

Full “quick prototype” set transported on the pickup and quickly downloaded on site. This was the first contact with the team. The activity was instantly dominated by the older women's group. Safety/protection tools were discarded along with unknown tools. Other equipment such as shovels, wheelbarrows, buckets and metal bars were taken immediately and started to be used.

SIMEX II Car with kit

- Free work of volunteers in the requested activities

At first the distribution of the activities among the volunteers facilitated the work. The men worked in the dismantling of construction elements and the women in the removal of debris. Then the roles were mixed and all the work was done in all the activities.

The work was mostly carried out without external participation, except for safety, where the use of specific material was marked along with a small demonstration for its correct use.

Mud and small debris were removed using a shovel, and wheelbarrow. In some cases the activity was complemented with the use of 30-litre buckets transported by two persons.

Large and heavy items were removed by hand using more volunteers if necessary. Interest in specific tools that can facilitate the work only came after the demonstration.

The volunteers carried out a classification of the removed materials into possible use and not possible use.

The mud and the small rocks were used to cover the holes in the street as an initiative of volunteers living in the neighborhood.

SIMEX II Simulation in progress

- Special explanations and demonstrations on request

Before SIMEX, a demonstration was held along with a technical explanation on the use and maintenance and history of the foot pump with the group of five volunteers supporting the stage preparation.

During SIMEX, specific demonstrations were held on the use of pulleys and individual safety elements.

- Open session after work UX comments and exchanges

The appreciation of the tools used was very positive because the materials available in the local market are of very poor quality.

Particular interest in demonstrations and trainings on how to use new tools such as the pulley, saw or foot pump.

Clear preference for 10 litre buckets because they are less heavy than 30 litre buckets and easier to transport.

Square head shovel preferred.

Outdoor burning of toxic plastics (PVC) is common practice.

Additional tools requested

Rake

Large hammer (90 cm handle)

SIMEX II scenario after works

- Used tools

| SIMEX II | USED ITEMS |
| --- | --- |
| 1 | Crow bar |
| 2 | Digging bar |
| 3 | Shovel (all models) |
| 4 | Wheelbarrow |
| 5 | Bucket 10l |
| 6 | Bucket 30l |
| 7 | Brush |
| 8 | Sledge Hammer 1k |
| 9 | Sledge Hammer 4k |
| 10 | Cask |
| 11 | Mask |
| 12 | Gloves |
| 13 | Goggles |

SIMEX 3

Location and scenario

The SIMEX 3 was located in a semi-rural village 1 hour distance from Antalaha using the main road. Exact location S14° 45’ 43”, E50° 12’ 58”

SIMEX 3

Collapsed construction

Build emergency Shelter

The scenario was an existing collapsed construction, including rest of wood, CGI, and a variety of elements dispersed on the site. Therefore, scenario preparation not needed.

SIMEX III scenario

SIMEX Follow up

- Introductory meeting explaining the objectives and definitions

The introductory session was conducted with the participation of volunteers and community members who were interested in the simulation. This community collaborated with CARE on shelter programs in 2004 and 2014. Some of the volunteers were previously trained as carpenters during the implementation of these programs.

The challenges proposed were to clean up the site where the construction collapsed, classify materials and build an emergency shelter using "quick prototype" equipment.

SIMEX III introduction

- Download and open the kit from the truck

All items where quickly downloaded from the pickup and organized in line for explanation and selection.

The explanation of each material was carried out from one of the trained volunteers. Other volunteers have participated actively with questions and asking for demonstrations.

Particular interest showed up regarding the revers cut saw. All young carpenters made several questions. In general, the rest of volunteers showed interest in the security equipment.

SIMEX III downloading the kit

- Free work of volunteers in the requested activities

Volunteers quickly organized following the instructions of the carpenters and divided into two teams. The first one to clean and classify materials, the second to start the work with the main pieces of the emergency shelter.

The first team classified the materials according to the possibility to be used in construction with a clear division between wood and the rest of the elements. The carpenters’ team started to work on the wood boxes for joints and for that, they have introduced their own tools.

After material classification, all teams joined in the construction of the emergency shelter that they agreed on the technique of traditional houses in the village, which includes wood structure, roof with natural leaves and walls with rushes and bamboo.

SIMEX III building emergency shelter

- Special explanations and demonstrations on request

Experienced carpenters made several demonstrations to the younger ones. In particular on the use of small tools and security elements.

One item caught the attention of the group of volunteers who took turns to test the revers-cutting saw. The particular shape and high performance of this tool was much appreciated.

SIMEX III explanations with new tools

- Open session after work UX comments and exchanges

New tools/items much appreciated from the volunteers. In particular young carpenters interested in the revers cut hand saw and the pulley system.

Refresher training for carpenters requested.

Shovel with squared head preferred

Machete not sharped and with big blade discarded.

Tools requested

Carpenter square

Chisel and wood hammer

Level

Drill brace  (Berbiqui)

Rake

SIMEX III scenario after simulation

- Used tools

| SIMEX III | USED ITEMS |
| --- | --- |
| 1 | Crow bar |
| 2 | Digging bar |
| 3 | Axe |
| 4 | Hand saw reverse cutting |
| 5 | Machete |
| 6 | Shovel (all models) |
| 7 | Wheelbarrow |
| 8 | PE bags |
| 9 | Brush |
| 10 | Cask |
| 11 | Gloves |
| 12 | Boots |
| 13 | Rope 10mm |
| 14 | Carpenter Hammer 250gs |
| 15 | Sledge Hammer 1k |
| 16 | Nails 50 and 100mm |
| 17 | Head nails |
| 18 | Stairs |
| 19 | Rope 6 and 10mm |
| 20 | Bucket 10l |
| 21 | Measuring tape 5m |
| 22 | Clippers |
| 23 | Metallic wire |
| 24 | Hand saw* |
| 25 | Square* |
| 26 | Chisel + wood hammer* |
| 27 | Drill brace (Berbiqui)* |

Note *These items were provided by the local carpenters

Final outputs from the SIMEX

The set of SIMEXs  have proven successful as an empirical validation mechanism.

Summarizing the SIMEX outputs:

- Avoid the use of tools/articles requiring maintenance or involving mechanical components. This was one of the main design bases verified with SIMEX exercises.

- The introduction of new technologies or techniques with elements unknown to users would pose an additional challenge and reduce the effectiveness of the kit.

- Basic training is required, including demonstrations and follow-up.

- Additional special training is required if alternative/new items are included in the kit.

- A basic list of hard items is commonly accepted and used in different SIMEX and contexts. This list of common elements partially validated the composition of the list of "rapid prototypes". Most of the elements not validated during this process will be removed from the final list. Only new items with a specific justification or a clear need remain on the final list.

- Additional items such as rake or carpenter's set have been identified and may be part of the final kit list.

- Additionally, SIMEX has provided a parameter to define the number of items in the final kit that will be based on a group of 10 users. This number can be multiplied depending on the size of the community.

6. The Community Shelter Kit

6.1 General information

The Community Shelter Kit is designed for immediate use after a disaster, supporting the capacities of the affected population. Specifically designed to be deployed (pre-positioned) in rural areas of the tropical Africa region, the CSK is dimensioned based on a team of 10 users that can be multiplied according to the size of the community. It is designed for community use with a theoretical size of 500 people.

The Community Shelter Kit matches the following requirements

| Requirement | Criteria |
| --- | --- |
| Context | Rural communities of tropical Africa |
| Type of associated disaster | Cyclones – floods |
| Type of response | immediately after the disaster -before international aid |
| Testing | Madagascar |
| Target community size | 500 people max. |
| Exclusion criteria | Mechanical, electric, new technologies or items that require maintenance. |
| Additional criteria | Prepositioning and transportability |

6.2 Community Shelter Kit list of items

The list below shows CSK items for a module for ten users. The number of items can be adapted according to the size of the community.

|  | CSK - ITEM LIST | Quantity |
| --- | --- | --- |
| 1 | BAG, coated woven PE, for rubble, 100L, 100g/m2 | 20 |
| 2 | BOOTS, heavy duty plastic rubber, pair, size 44 | 10 |
| 3 | GLOVE, protection, heavy duty soft leather, size 11, pair | 10 |
| 4 | GOOGLES, plastic, with rubber string, eyes protection | 10 |
| 5 | HELMET, builder, plastic, white, size 51-62 | 10 |
| 6 | MASK, vapor and dust protection, FPP2 disposable half mask | 10 |
| 7 | TIE WIRE, galvanized, diam. 1.5 mm, 25m, roll | 2 |
| 8 | BUCKET, heavy duty rubber, masonry type 10l | 6 |
| 9 | CROWBAR, with angled beak, 500 mm length | 2 |
| 10 | DIGGING BAR, 1.6m | 2 |
| 11 | SLEDGE HAMMER, hardened steel, short wood handle, 1000g, 250mm | 4 |
| 12 | SLEDGE HAMMER, hardened steel, long wood handle, 4800g, 900mm | 2 |
| 13 | WHEEL BARROW, approx. 90L dry solids, strong solid wheel | 3 |
| 14 | ARCH SAW, bow type, for wood, 750mm blade from green wood | 2 |
| 15 | Hand saw "revers cutting" for bamboo + green wood | 2 |
| 16 | Machete wood handle | 4 |
| 17 | BROOM, floor washing broom, long handle | 6 |
| 18 | ROPE, POLYPROPYLENE, black, diam. 12mm, twisted, roll 100m | 1 |
| 19 | Power puller with tendon and hook, max, load 3000k | 1 |
| 20 | AXE, 1,5kg head with safety handle, 900mm | 2 |
| 21 | SHOVEL, rectangular head with long handle | 6 |
| 22 | First aid kit | 1 |
| 23 | Tarp 4x6 standard IFRC | 4 |
| 24 | Nails 120mm, 5kg box | 2 |
| 25 | Head nails for roofing, 5g box | 1 |
| 26 | Measuring tape 5m | 2 |
| 27 | Carpenter chisel flat 20mm | 2 |
| 28 | SQUARE, carpenter type, 250mm, steel | 2 |
| 29 | Hand drill brace (barbeque) | 1 |
| 30 | Claw hammer | 4 |
| 31 | LAMP, SOLAR led for familly, Li-ion battery | 4 |
| 32 | LADDER, aluminum foldable in 4 parts, 4.5m | 1 |
| 33 | MEGAPHONE, 25W, connect. on cigar lighter and batteries | 1 |

6.3 Logistics and items price

Availability on the local markets of all the materials for the Community Shelter kit was confirmed during the Madagascar mission.

The estimative price of the Community Shelter Kit for this basic module for 10 users would have important variations according to the precedence and quantity of the modules to purchase.

In order to avoid possible deviations and to facilitate the selection and acquisition of the suitable items, it is recommended to follow the individual items description that is referred to in the SPC.

The following list shows the price per unit in Madagascar market.

|  | CSK - ITEM LIST | Quantity | Ariar | Total |
| --- | --- | --- | --- | --- |
| 1 | BAG, coated woven PE, for rubble, 100L, 100g/m2 | 20 | 2000 | € 10.00 |
| 2 | BOOTS, heavy duty plastic rubber, pair, size 44 | 10 | 40000 | € 100.00 |
| 3 | GLOVE, protection, heavy duty soft leather, size 11, pair | 10 | 5075 | € 12.69 |
| 4 | GOOGLES, plastic, with rubber string, eyes protection | 10 | 3375 | € 8.44 |
| 5 | HELMET, builder, plastic, white, size 51-62 | 10 | 16667 | € 41.67 |
| 6 | MASK, vapor and dust protection, FPP2 disposable half mask | 10 | 197 | € 0.49 |
| 7 | TIE WIRE, galvanized, diam. 1.5 mm, 25m, roll | 2 | 34583 | € 17.29 |
| 8 | BUCKET, heavy duty rubber, masonry type 10l | 6 | 35000 | € 52.50 |
| 9 | CROWBAR, with angled beak, 500 mm length | 2 | 145000 | € 72.50 |
| 10 | DIGGING BAR, 1.6m | 2 | 30450 | € 15.23 |
| 11 | SLEDGE HAMMER, hardened steel, short wood handle, 1000g, 250mm | 4 | 19692 | € 19.69 |
| 12 | SLEDGE HAMMER, hardened steel, long wood handle, 4800g, 900mm | 2 | 220000 | € 110.00 |
| 13 | WHEEL BARROW, approx. 90L dry solids, strong solid wheel | 3 | 280000 | € 210.00 |
| 14 | ARCH SAW, bow type, for wood, 750mm blade from green wood | 2 | 10240 | € 5.12 |
| 15 | Hand saw "revers cutting" for bamboo + green wood | 2 | 240000 | € 120.00 |
| 16 | Machete wood handle | 4 | 4812 | € 4.81 |
| 17 | BROOM, floor washing broom, long handle | 6 | 25200 | € 37.80 |
| 18 | ROPE, POLYPROPYLENE, black, diam. 12mm, twisted, roll 100m | 1 | 303192 | € 75.80 |
| 19 | Power puller with tendon and hook, max, load 3000k | 1 | 13000 | € 3.25 |
| 20 | AXE, 1,5kg head with safety handle, 900mm | 2 | 35000 | € 17.50 |
| 21 | SHOVEL, rectangular head with long handle | 6 | 11500 | € 17.25 |
| 22 | First aid kit | 1 | 80000 | € 20.00 |
| 23 | Tarp 4x6 standard IFRC | 4 | 165000 | € 165.00 |
| 24 | Nails 120mm, 5kg box | 2 | 95835 | € 47.92 |
| 25 | Head nails for roofing, 5g box | 1 | 69125 | € 17.28 |
| 26 | Measuring tape 5m | 2 | 7833 | € 3.92 |
| 27 | Carpenter chisel flat 20mm | 2 | 40000 | € 20.00 |
| 28 | SQUARE, carpenter type, 250mm, steel | 2 | 150000 | € 75.00 |
| 29 | Hand drill brace (barbeque) | 1 | 7833 | € 1.96 |
| 30 | Claw hammer | 4 | 8200 | € 8.20 |
| 31 | LAMP, SOLAR led for family, Li-ion battery | 4 | 180000 | € 180.00 |
| 32 | LADDER, aluminum foldable in 4 parts, 4.5m | 1 | 324892 | € 81.22 |
| 33 | MEGAPHONE, 25W, connect. on cigar lighter and batteries | 1 | 150000 | € 37.50 |
|  |  |  |  | € 1,610.02 |

- The price in the local market of Antananarivo in July 2019 of the module “10 users” of the Community Shelter Kit is 1610.02 Euros

6.4 CSK Items description

The list below shows the CSK items with the specific code linked with the IFRC Standard Product Catalogue.

By clicking on the following link, the technical specifications of each of the articles can be accessed. (https://itemscatalogue.redcross.int/index.aspx).

|  | CSK ITEM | SPC CODE |
| --- | --- | --- |
| 1 | BAG, coated woven PE, for rubble, 100L, 100g/m2 | APACBAGPR09 |
| 2 | BOOTS, heavy duty plastic rubber, pair, size 44 | APROBOOTR44 |
| 3 | GLOVE, protection, heavy duty soft leather, size 11, pair | APROGLOVHD11 |
| 4 | GOOGLES, plastic, with rubber string, eyes protection | APROGOOGPL |
| 5 | HELMET, builder, plastic, white, size 51-62 | APROHELM7 |
| 6 | MASK, vapor and dust protection, FPP2 disposable half mask | APROMASKDGD |
| 7 | TIE WIRE, galvanized, diam. 1.5 mm, 25m, roll | EHDWWIRETR15 |
| 8 | BUCKET, heavy duty rubber, masonry type 10l | ETOOBUCKR10 |
| 9 | CROWBAR, with angled beak, 500 mm length | ETOOCROBA500 |
| 10 | DIGGING BAR, 1.6m | ETOODIGB1602 |
| 11 | SLEDGE HAMMER, hardened steel, short wood handle, 1000g, 250mm | ETOOHAMMSL10 |
| 12 | SLEDGE HAMMER, hardened steel, long wood handle, 4800g, 900mm | ETOOHAMMSL48 |
| 13 | WHEEL BARROW, approx. 90L dry solids, strong solid wheel | ETOOWHEBS90L |
| 14 | ARCH SAW, bow type, for wood, 750mm blade from green wood | ETOOSAWSW750 |
| 15 | Hand saw "revers cutting" for bamboo + green wood | No Code available |
| 16 | Machete wood handle | RAGRTOOLMAC1 |
| 17 | BROOM, floor washing broom, long handle | HHYGCLEMBRWF |
| 18 | ROPE, POLYPROPYLENE, black, diam. 12mm, twisted, roll 100m | HSHEROPE12PB |
| 19 | Power puller with tendon and hook, max, load 3000k | ETOOPULLH15L30 |
| 20 | AXE, 1,5kg head with safety handle, 900mm | RAGRTOOLAXE2 |
| 21 | SHOVEL, rectangular head with long handle | RAGRTOOLSHO2 |
| 22 | First aid kit | KMEDKFAI01C |
| 23 | Tarp 4x6 standard IFRC | HSHETARPW406 |
| 24 | Nails 120mm, 5kg box | EHDWNAILW120 |
| 25 | Head nails for roofing, 5g box | EHDWNAILRS01 |
| 26 | Measuring tape 5m | EMEATAPMRO52 |
| 27 | Carpenter chisel flat 20mm | ETOOCHISWF20 |
| 28 | SQUARE, carpenter type, 250mm, steel | EMEAMETASQR2 |
| 29 | Hand drill brace (barbeque) | EMACDRILHBRA |
| 30 | Claw hammer | ETOOHAMMCARW |
| 31 | LAMP, SOLAR led for family, Li-ion battery | EELELAPOFAM1 |
| 32 | LADDER, aluminum foldable in 4 parts, 4.5m | ETOOLADDEX45 |
| 33 | MEGAPHONE, 25W, connect. on cigar lighter and batteries | ASECMGPH1 |

6.5 Prepositioning of items

The preposition of CSK items would include, among other things, ensuring the availability of these items when the community needs them (prepositioning of items is different from delivery).

The items in the CSK do not include mechanical components and it is not required to store combustibles. This characteristics facilitate the CSK storage for a long period in normal warehousing conditions.

Therefore, the storage conditions are key to ensure the good condition of the materials. In this sense, it is possible to point out the importance of the minimum following requirements

- The storage space has to be dry, providing protection against rain, floods or other possible infiltrations

- Shade space covered from solar radiation (UV)

- Ventilated, ensuring the air renovations

- Clean and easy to maintain

- Ensure the security of materials (theft prevention)

Existing constructions that meet the defined requirements would be a good option for storing CSK elements. New constructions that respect traditional building types can also be a good alternative. Alternatively, prefabricated solutions can be explored as a mini-container.

Example picture- abccontainers.com

This storage solution matches with the predefined requirements and provides an alternative for a storage place that can be easily replicated in the region.

7. Conclusions

7.1 Climatic and geographic context

Northern Madagascar, in particular, the Antalaha region, is part of the defined tropical Africa region. It is possible to find an important variety of climatic and geographical situations in the predefined region. In this context, the CSK shows great flexibility in terms of availability in the local market of the items identified. An additional value is the good acceptance of the articles by the users. The direct validation of the articles during the mission provided a clear positive indicator. Therefore, the CSK will provide an effective tool to strengthen community resilience.

7.2 Community Shelter kit response

The development of a "Regional Community Shelter Kit" required a particular strategy. The CSK appears as a validated and flexible tool for the community. The concept proposes a series of items that, combined, respond adequately to the identified functions. The immediate disposition of the articles provides great flexibility to the community's response. It is expected to bring effective results in different contexts, from rural to semi-rural. With adequate training and awareness, the CSK will provide a flexible and effective community emergency response.

7.3 Operational flexibility

The concept of the proposed CSK offers the possibility of proposing a complete combination of basic items in a module of 10 users or simply increasing the size by multiplying the module according to the requirements of the community. This complementary approach would facilitate the response to different situations in a wider geographical area of the identified region. Also, this kit concept facilitates small adaptations according to the requirements of the community and the availability of the material in the market. To support this flexibility it would be required to provide a person or team that responds to the maintenance of the kit and the management of the items.

8. Operational challenges

8.1 Inside country restrictions

The mission was from Antananarivo to Antalaha. All locations allowed the proper functioning of the mission and equipment in a safe context. The materials were purchased in Antananarivo and transported to Antalaha more than 1000 km north due to the non-availability of the materials on the project site. This geographical limitation represented a challenge for the logistical organization of the mission. At the same time, it shows the relevance of the project concept with the preposition of CSK elements at strategic points.

8.2 Timeframe

The time for the project was the result of a long process of coordination with AI-CRL and IFRC-SRU. The last modification of the service contract was agreed and signed in January 2019. This period of exchange and coordination unfortunately had a direct impact on the time available for project implementation.

8.3 Geographic limitations

The originally proposed regional project was designed with missions to different countries. After discussion, the project was changed to a validation mission in Madagascar. The mission, carried out in July 2019, has provided good indicators and validation of the items based on the context of Antalaha in Madagascar. The assumption, for project proposal, is that the validation obtained can be translated into a similar context in the region.

9. Recommendations

9.1 Regional expansion

It is possible to find common denominators in the rural context of the tropical region of Africa for which the CSK is designed. The urban context of the same African region presents different characteristics, dynamics, and needs. High population density, damaged or non-existent infrastructure, weak or non-adapted buildings are just some of the common denominators of urban areas. This shows that needs and capacities are different from those of rural areas. Therefore, to cover the region and, in particular, the largest number of vulnerable people, a new project will be recommended which, following a similar procedure, will focus on the development of a CSK for urban areas in the same region.

9.2 Replication and adaptation

Proven experiences like IFRC- Shelter kit showed that a regional shelter solution demands small key adaptations to be effective in the different countries in the region. The proposed items for the CSK verified during the IFRC-SRU Madagascar mission would provide an effective response in a similar context. During the CSK project and in particular the Madagascar mission a specific procedure of design and participative validation was implemented. Specific measures within future small projects that repeat the defined procedures can be undertaken to ensure the effectivity of the CSK to the different shelter operations and context.

9.3 Training packages

The design of the CSK proposes an innovative and flexible approach in which the shelter kit is the combination of different items. With the availability of all the items in the local markets the CSK concept would provide an effective tool to the community to respond before national or international aid implement the operation of emergency shelters. The experience gained during the implementation of other shelter kits shows that the delivery of specific and tailored training packages is a key factor to maximize the impact of the community use of the CSK.

Therefore, to support future shelter operations in which CSK will be implemented, a set of face-to-face training packages should be delivered. Alternatively, these training courses/workshops would be completed with online modules.

10. Annexed documents

Service agreement

Terms of Reference

List of contacted people

| Date | Nom | Position | Telf. | Mail |
| --- | --- | --- | --- | --- |
| 03.07.2019 | Andoniaina Ratsimamanga | GS - MRC | 261320419402 | sg@crmada.org |
| 03.07.2019 | Nahavitatsara Angelo | MRC- head of WATHAB | +261 344300964 | nahavitatsara@gmail.com |
| 04.07.2019 | Youcef Ait Chellouche | IFRC head of Indian ocean island | +261327789507 | youcef.aitchellouche@ifrc.org |
| 12.07.2019 | Aritiana Faly | Coordonateur des Programes d’urgence BNRC- Madagascar | +261340548067 | Aritiana23@gmail.com |
| 16.07.2019 | CNE. Andrimitantsoa Haja | Deputy Executve Secretary | +261 202264472 | handriamitantsoa@yahoo.fr |