## Instructions and guidance
Guidance on completing the Indicator Tracking Table - taken from the IFRC's M&E guide: annex 16, pages 110-111
ITT purpose and compliance
The ITT is an important data management tool for recording and monitoring indicator performance. It informs project/programme implementation and management, tracking progress towards specific targets for better transparency and accountability within and outside the IFRC.
The ITT should be included as a critical part of regular project/programme management reports. The report’s narrative should explain the data recorded in the ITT, including any significant variance in indicator performance (difference between targets versus actual performance - especially any variance greater than ten per cent. Sections may be included directly in the report, and the complete ITT may be included as an annex in the report.
Typically, the ITT is completed by project/programme team members and submitted by the project/programme manager.
This ITT format is to be used by all secretariat-funded projects/programmes at the field level, and is to inform other indicator reporting formats within the secretariat and the larger IFRC community as appropriate.
ITT submission should follow the agreed (required) frequency and reporting lines according to the specific project/programme. Typically the ITT is completed on a quarterly reporting basis, as the spreadsheet is currently formatted. However, for shorter projects/programmes, it can be reformatted to a monthly basis.
ITT instructions
ITT format
Initial set-up of the ITT for a specific project/programme will take some time, but thereafter it will be easier to complete.
The ITT is designed and managed in an Excel worksheet that contains all of the objectives of the project/programme logframe, with indicators listed under their objectives. The Excel worksheet for the IFRC’s ITT can be accessed at the IFRC’s webpage for M&E: www.ifrc.org/MandE
Excel formulas have been embedded in the following cells of the ITT worksheet.
  Life of Project Actual,
  % of Life of Project Target
  Year to date Actual,
  % of Annual Target
  All % of quarterly targets.
These formulas make automatic calculations and therefore reduce the amount of data that must be entered manually. However, even with the help of formulas to automatically calculate, it is important to be careful that the data has been calculated as intended. Adjustments will often have to be made to suit the particular time frame and other aspects of the project.
If there are problems with the formulas, you may need to re-enter them. If necessary, seek the assistance of someone experienced with Excel, or through the guidance and help available in Excel.
As the ITT mirrors the project/programme logframe, the listed objectives and indicators in the worksheet should remain the same throughout the life of the project/programme (unless the logframe itself is to be changed).
Additional guidance for the ITT and the overall M&E system can be found in the IFRC’s project/programme M&E guide (see www.ifrc.org/MandE).
ITT completion – overall reminders
Data reported in the ITT should be confirmed for the reporting period, and not made up of estimates or guesses. If you are confused about what an indicator means or how to report on it, refer to your project/programme M&E plan.
Values for indicators should be numeric with descriptions reserved for the narrative report.
Remember that “0”, “NA” and “UK” all mean different things. Entering “0” means that no progress was made against an indicator for the given time period. If your project/programme does not measure an indicator for a given time period (e.g. no target was set), enter “NA” (not applicable). Only enter “UK” (unknown) for instances where an indicator target has been set, but the indicator can not be measured due to missing or unreliable data (e.g. the M&E system may not be in place yet).
For indicators that are measured in percentages, enter the numerator and denominator as a ratio and then format the cell as a percentage (e.g. 50 per cent, not 0.5). This ensures that all of the relevant data is entered into the ITT.
A new ITT worksheet should be added for each new project/programme year as needed. If you do this, the "life of project" formulas will need to be revised accordingly.
Project/Programme background information
Project/Programme Name: Enter the project/programme name used in the proposal.
Project/Programme No. or ID: Enter the project/programme number or ID.
Project/Programme Manager: Enter the project/programme manager’s name.
Project/Programme Sector: Select the appropriate project/programme sector, e.g. disaster management.
Project/Programme Location: Enter the field location of where the project/programme is being implemented (e.g. district(s) and/or province and country).
Reporting Period: Enter the reporting period for which the ITT is being completed.
Project/Programme Start Date: Enter the date for when the project/programme implementation will begin.
Project/Programme End Date: Enter the expected date for when the project/programme will end.
Federation-Wide Databank and Reporting System (FDRS) indicators (Click here for more guidance on how to collect these indicators on FedNet (IFRC's intranet - account required): . Annual data available on http://www.ifrc.org/data)
The FWRS indicators allow us (IFRC) to annually report on our global performance across project/programme areas and locations. However, they are an important aspect of project/programme performance and should be monitored and reported on in any case.
The FWRS indicators only need to be reported on an annual basis, but the project/programme can monitor them according to its own needs. It is likely that the indicator values will be determined at the end of the calendar year, corresponding with the FWRS reporting requirements.
The FWRS indicator guide should be carefully consulted to ensure that indicator reporting is consistent and accurate. Measuring the FWRS indicators can be tricky, especially due to issues of double-counting and direct/indirect recipients. Therefore, use the FWRS indicator guide, and it may be necessary to seek the technical assistance of an IFRC FWRS resource person.
As the FWRS indicators do not need to be reported on a quarterly basis, their measurement will likely be determined from a review of the existing indicator performance (and with caution to avoid double-counting according to the FWRS indicator guide).
Targets for the FWRS indicators are recommended for people reached, and up to the project/programme’s management for the other indicators.
Logframe objective and indicators statements
Enter the project/programme statements for the project/programme goal, outcome(s), outputs, and indicators as they appear in the logframe.
Logframe indicator reporting
Project/programme baseline date/value – Enter the date of the project/programme baseline and value for this indicator. If a baseline has not yet been conducted but is planned, leave this blank. If no baseline will be conducted or no data is required for a particular indicator, write “NA” (for “not applicable”). Remember, not all indicators will need to be measured during the baseline. For instance, in example indicator 1.2a and 2.1a, the value is zero because participating communities and schools had not developed any disaster management plans.
Target – Targets should be set for each quarter and are usually entered into the indicator tracking sheet during the same time period as the planning of the annual project budget for the next year. If your project/programme does not measure (set a target) an indicator for a respective quarter, enter “NA” not “0”. For instance, in example indicator 2.1a, targets are “NA” because community disaster management plans had not yet been developed to be tested.
Actual – Enter the actual indicator value for the current reporting period. Enter only accurate data, not estimated data. Entering “0” means that no progress was made against an indicator for the given time period. If your project/programme does not measure this indicator for a respective quarter, write “NA”. Enter “UK” (unknown) for instances where an indicator target has been set, but the indicator cannot be measured due to missing or unreliable data (e.g. the M&E system may not be in place yet). For instance, in example indicator 1.a, for the first quarter, the target was set at identifying 50 people in participating communities, but it was not possible to measure this indicator for this quarter because some data was missing. This type of issue can be explained in the project/programme management report which should use the ITT to report on progress.
Percentage of target – This cell has a formula to automatically calculate the percentage of the target that was actually achieved by the indicator during the reporting period (by dividing actual by the target). Double check in the first instance to make sure that the percentage is accurate and that the formula is working correctly. In example indicator 2.2a for the second quarter, the number of students in the targeted schools who received disaster preparedness and disaster risk education was larger than the original target set for Q2 for that indicator which resulted in a percentage of target of 130 per cent. This sometimes happens that the actual performance will under- or over-perform the stated target. Such variance should be explained in the regular project/program report which should use the ITT to report on progress.
Annual target – Annual targets are entered into this column at the start of the project/programme. All annual targets should be included in each annual indicator tracking sheet. Annual targets for individual indicators may be revised at the end of the year to reflect major programmatic changes/revisions. However, revisions should not affect total life of project targets, and any revision should be authorized (e.g. approved by the donor). See Annual targets in indicators 1a, 1.1a, 1.2a, 2a and 2.2a.
Year to date actual – This value will change each quarter there has been indicator performance. Depending on the indicator, you may want to create a formula to tabulate this automatically. Some indicators may need to be calculated manually (e.g. where the actual is not the sum of all quarterly actuals but the highest number). See Year to date actuals in indicators 1a, 1.1a, 1.2a, 2a and 2.2a.
Percentage of annual target – This cell has a formula to automatically calculate this value by dividing the Year to date actual by the Annual target. Double-check to make sure that this is the accurate percentage and that the formula is working correctly. See Percentage of annual target in indicators 1a, 1.1a, 1.2a, 2a and 2.2a.
Life of project (LoP) target – LoP targets are entered into this column at the start of the project/programme. All LoP targets should be included in each annual indicator tracking sheet. Generally, LoP targets should not be revised except under rare instances, and with the proper authorization (e.g. from donors). See LoP targets in indicators 1a, 1.1a, 1.2a, 2a and 2.2a.
Life of project actual – This value will change each quarter there has been indicator performance. Depending on the indicator, you may want to create a formula to tabulate this automatically. Some indicators may need to be calculated manually (e.g. where the LoP actual is not the sum of all quarterly actuals but the highest number). See LoP actuals in indicators 1a, 1.1a, 1.2a, 2a and 2.2a.
Percentage of LoP target – This cell has a formula to automatically calculate this value by dividing the actual to date by the life of project/programme target. Double-check to make sure that this is the accurate percentage and the formula is working correctly. See Percentage of LoP target in indicators 1a, 1.1a, 1.2a, 2a and 2.2a.

## ITT - with examples (for 1 year
Project/Programme Indicator Tracking Table (ITT)*
Project/Programme Name
Project/Programme Manager | [6 empty] | Reporting Period
Project/Programme #/ID | [6 empty] | Project/Programme Start Date
Project/Programme Location | [6 empty] | Project/Programme End Date
Project/Programme Sector | [6 empty] | Extra Field
Federation-Wide Databank and Reporting System (FDRS) Indicators - see annual data at www.ifrc.org/data | [10 empty] | See this Fednet link for guidance on FDRS
People Reached |  |  |  |  | Total People Covered |  | Volunteers |  |  | National Society Paid Staff |  |  | Secretariat Paid Staff
Direct |  |  | Indirect | Grand Total
Women | Men | Total | Total |  |  |  | Women | Men | Total | Women | Men | Total | Women | Men | Total
Project/Programme Logframe Indicators
INDICATOR |  |  |  | Project Baseline |  | LoP Target | LoP Actual | % of LoP Target | Annual Target | Year to Date Actual | % of Annual Target | Q1 Reporting Period |  |  |  | Q2 Reporting Period |  |  | Q3 Reporting Period |  |  | Q4 Reporting Period
|  |  |  | Date | Value | [6 empty] | Target | Actual | % of Target |  | Target | Actual | % of Target | Target | Actual | % of Target | Target | Actual | % of Target
Goal
Ga. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Outcome1. Example - Improve community capacity to prepare for and respond to disasters.
1a. Example - % people in participating communities who pracitce 5 or more disaster preparedeness measures identified in the community disaster management (DM) plan. |  |  |  | 2011-12-01 | 10% | 80% | 45% | 56.25% | 80% | 45% | 56.25% | 50% | UK | 0% |  | 60% | 30% | 50% | 70% | 45% | 64.29% | 80% |  | 0%
Output 1.1. Example - Improved community awareness of measures to prepare for and respond to diasters.
1.1a. Example - % people in participating communities who can identify at least 5 preparedeness and 5 response measures. |  |  |  | 2011-12-01 | 20% | 70% | 55% | 78.57% | 70% | 55% | 78.57% | 40% | 20% | 50% |  | 50% | 30% | 60% | 60% | 55% | 91.67% | 70% |  | 0%
Output 1.2. Example - Community Disaster Management Plans are developed and tested by Community Disaster Management Committees.
1.2a. Example - # of participating communities that have a tested Disaster Management Plan. |  |  |  | 2011-12-01 | 0 | 100 | 23 | 23% | 50 | 23 | 46% | 10 | 3 | 30% |  | 10 | 5 | 50% | 20 | 15 | 75% | 10 |  | 0%
Outcome 2. Example - School capacity to prepare for and respond to disasters is improved.
2a. Example - % of schools that have passed the annual disaster safety inspection from the Ministry of Disaster Management. |  |  |  | 2011-12-01 | 10% | 50% | 30% | 60% | 50% | 30% | 60% | 20% | 15% | 75% |  | 30% | 25% | 83.33% | 40% | 30% | 75% | 50% |  | 0%
Output 2.1. Example - School Disaster Management Plans are developed and tested at participating schools.
2.1a. Example - # of participating schools that have a new DM plan tested. |  |  |  | 2011-12-01 | 0 | 100 | 30 | 30% | 45 | 30 | 66.67% | NA | NA | 0% |  | 10 | 5 | 50% | 15 | 10 | 66.67% | 20 | 15 | 75%
Output 2.2. Example - Disaster risk reduction lessons are included in the curriculum.
2.2a. Example - % of students in the targeted schools who have received disaster preparedness and disaster risk education. |  |  |  | 2011-12-01 | 25% | 75% | 35% | 46.67% | 50% | 35% | 70% | 25% | UK | 0% |  | 30% | 25% | 83.33% | 40% | 35% | 87.5% | 50% |  | 0%
Output 2.3
2.3a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
2.3b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
2.3c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Outcome 3
3a. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3b. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3c. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Output 3.1
3.1a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3.1b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3.1c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Output 3.2
3.2a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3.2b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
1.2c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Output 3.3
3.3a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3.3b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
3.3c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Outcome 4
4a. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4b. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4c. | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Output 4.1
4.1a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4.1b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4.1c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Output 4.2
4.2a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4.2b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4.2c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Output 4.3
4.3a | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4.3b | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
4.3c | [7 empty] | 0% |  |  | 0% |  |  | 0% |  |  |  | 0% |  |  | 0% |  |  | 0%
Add rows for additional objectives and indicators as needed.
The ITT should be included as a critical part of regular project/programme management reports.
The report’s narrative should explain the data recorded in the ITT, including any significant variance in indicator performance (difference between targets versus actual performance).
This ITT has example objectives and indicators, but they are only examples without a full list of a project's objectives and indicators. Please note that the FDRS indicators need only be recorded annually.
Please note that this ITT Excel spreadsheet and other versions with formulas for calculation is available at www.ifrc.org/MandE
Note on N12: Use this field if you need to include any addition information.
Note on C14: Comment: Key indicators gathered on an annual basis to reliably monitor and report on IFRC's collective work as part of the Federation-Wide Databanka nd Reporting System (FDRS).
Note on C15: Comment: Direct and indirect recipients and people covered by Federation services, disaggregated by service areas.
Note on H15: Comment: People that are targeted by a programme for which the benefit is not immediate, but from which the target population can benefit if an adverse event occurs.
Note on J15: Comment: People that have volunteered at least four hours during the annual reporting period with the Red Cross and Red Crescent.
Note on M15: Comment: People who work with a National Society for a minimum of three months and are remunerated.
Note on P15: Comment: People who work with the secretariat for a minimum of three months and are remunerated.
Note on C16: Comment: Countable recipients of services from a Federation provider at the delivery point.
Note on F16: Comment: Recipients that cannot be directly counted because they receive services apart from the provider and the delivery point.
Note on J27: Comment: This formula automatically shows the most recent "life of project" value for this example. As only one year is shown, the life of project and annual values are the same. For a multi-year project / programme, the life of project values would have to be the cumulation of the data from all quarters for all years. The formulas would have be to modified accordingly.
Note on J31: Comment: Note that this Annual / Life of Project target is calculated cumulatively. However, the quarterly actual and % of target for this indicator are counted non-cumulatively - each quarter's target and actual is not added to the previous quarter. Example 2.1 below is also counted non-cumulatively per quarter. The other indicators are counted cumulatively each quarter - each quarter's value is based on the previous quarter.
Note on J35: Comment: Note that this Annual / Life of Project target is calculated cumulatively - but quarterly actual and % of target are non- cumulative (each quarter's target and actual is not added to the previous quarter) The first quarter is omitted from the formula as that data is "not applicable"
Note on M35: Comment: Same formula used here for quarterly data counted non-cumulativey by quarter, but the first quarter (cell P35) is omitted as it is "not applicable"