## Slide 1
DATA RESPONSIBILITY - ROADMAP
Aug 2017
25th May 2018: enforcement GDPR

## Slide 2
DATA RESPONSIBILITY – RELEASE OF POLICY
Aug 2017
Release of:
Data Responsibility Policy (public)
Checklist (internal)
Threat & Risk analysis (internal)

## Slide 3
DATA RESPONSIBILITY – MORE THAN GDPR
Aug 2017
Data Responsibility includes:
Data protection
Ethical standards
Humanitarian context
Based on 7 principles:

## Slide 4
DATA RESPONSIBILITY – MORE THAN GDPR
Aug 2017

## Slide 5
DATA RESPONSIBILITY – ACTIVITIES SEP – DEC ‘17
Sep - Dec 2017
Activities:
Awareness Training of Team
External data literacy workshops
Collection of Feedback
25th May 2018: enforcement GDPR

## Slide 6
DATA RESPONSIBILITY – INITIAL FEEDBACK
Jan 2018
25th May 2018: enforcement GDPR
Main feedback & insights:
“We’re lacking practical tools to deal with PII and DII data”
“Which role(s) do team members have for handling data?”
“Continue to learn from each other and from each other’s projects”

## Slide 7
DATA RESPONSIBILITY - LEARNINGS
Jan 2018 – March 2018
25th May 2018: enforcement GDPR
Learnings from Cash Transfer projects:
Data is often not destroyed after serving its purpose.
It is often shared without checking purpose and consent given.
Cleaning of data is often not done.

## Slide 8
DATA RESPONSIBILITY - LEARNINGS
May 2018
Learnings from Irma response St Maarten:
Do not use Google drive for storing personal data.
If Google drive is used then apply good password management.
Jan 2018 – March 2018

## Slide 9
DATA RESPONSIBILITY – SIMPLIFY & STANDARDIZE
Jan - April 2018
Centralized data repository implemented: MicroSoft Azure.
Internal comms solution implemented: MicroSoft Teams.
(Re)-use of templates.
Updated version of DR policy document in progress.
25th May 2018: enforcement GDPR

## Slide 10
DATA RESPONSIBILITY – ACTIVITIES MAY
May 2018
Planned delivery: updated version of DR policy document.
Planned delivery of updated checklist.
Continuation internal and external communications.
25th May 2018: enforcement GDPR

## Slide 11
Thank you!